| Project Status Report |  |
| --- | --- |
| Project Name | South Saskatchewan Community Foundation (SSCF) Resource Hub |
| For Week Ending | March 15, 2025 |
| Project Status | Yellow |
| Status Description | The project is progressing well, but there are a few areas that require attention to ensure timely completion: Reason for Yellow Status: - Responsive Design: the responsiveness and content is been worked upon while the hierarchy and site structure has been built. - Content Updates: Additional resources and learning materials need to be added to the Resources and Learning Opportunities sections. Planned Actions: - Refine the search functionality and other contents - Fix responsive design issues - Populate the Resources and Learning Opportunities sections with additional content. |
| Activities—During the Past Week |  |
| - High-Fidelity Prototype Development: - Completed the high-fidelity prototypes for both mobile and desktop modes. - Integrated the Hamburger menu for mobile navigation. - Added responsive design elements to ensure compatibility across devices. - User Story Map (USM) Updates: - Updated the USM to reflect the latest MVP features and unscheduled items. - Exported the USM as a PDF for documentation. - Formative Usability Testing: - Conducted usability testing with stakeholders using the high-fidelity prototype. - Collected feedback on key tasks (e.g., navigating to the "Fundraising" section, using the Business Directory). - Summarized insights from the usability testing - Content Development: - Added placeholder content for the Resources and Learning Opportunities sections. - Created a draft of the Business Directory with sample entries. |  |
| Activities—Planned for Next Week |  |
| - Refine Prototype Based on Feedback: - Improve the search functionality in the Business Directory. - Fix responsive design issues for the Hamburger menu in mobile view. - Content Population: - Add finalized content to the Resources and Learning Opportunities sections. - Populate the Business Directory with real data. - Additional Usability Testing: - Conduct a second round of usability testing with updated prototypes. - Gather feedback on the refined search functionality and responsive design. - Documentation: - Update the User Story Map (USM) to reflect any changes. - Prepare a final report summarizing usability testing insights and design decisions. |  |
| Project Issues |  |
| - Issue 1: Confusing Search Functionality in Business Directory Description: Users found it difficult to filter and search for services in the Business Directory. Action Plan: Redesign the search and filtering interface to make it more intuitive. - Issue 2: Hamburger Menu Responsiveness Description: The Hamburger menu in mobile view has minor alignment issues. Action Plan: Adjust the CSS and layout to ensure proper alignment and functionality. - Issue 3: Content Gaps in Resources Section Description: Some resources and learning materials are still in draft form. Action Plan: Finalize and upload all content by the end of next week. |  |
| Project Changes |  |
| Project Changes: - Change 1: Removal of VSCN Membership Feature - Description: The VSCN membership feature was deemed out of scope for this project. - Impact: This change allows the team to focus on core features like the Resources and Business Directory sections. - Change 2: Standalone Website Decision - Description: The resource hub will be a standalone website, not integrated into the existing SSCF website. - Impact: This decision simplifies development and ensures better performance. |  |